## Risk Register
Cloud GRC Risk Register
FinSecure Analytics Ltd. ¦ ISO/IEC 27001:2022 ¦ AWS Cloud Environment ¦ Semi-Quantitative Risk Scoring (Likelihood × Impact)
Risk ID | Risk Description | ISO Control | Likelihood (1-3) | Impact (1-3) | Risk Score (L×I) | Risk Level | Control / Treatment Plan | Residual Risk | Risk Owner
R1 | Public S3 Bucket Exposure Unauthorized public read/write access to sensitive data buckets | A.10, A.9 | 3 – High | 3 – High | 9 | HIGH | S3 Block Public Access enabled at account level. Lambda auto-remediation blocks public access within <2 min of detection. EventBridge rule monitoring PutBucketAcl events. | Low | Cloud Admin
R2 | Excessive IAM Permissions Over-privileged users creating privilege escalation risk | A.9 | 2 – Medium | 3 – High | 6 | MEDIUM | Least privilege IAM policies implemented. RBAC enforced with separate roles per function. IAM Access Analyzer runs monthly review. | Low | Security Team
R3 | Root Account Misuse Root account used for routine operations without MFA | A.9 | 1 – Low | 3 – High | 3 | LOW | MFA enforced on root account. AWS config does continuous monitoring. | Low | CISO
R4 | Configuration Drift AWS resources modified outside approved change process | A.12 | 3 – High | 2 – Medium | 6 | MEDIUM | AWS Config rules continuously evaluate 5+ compliance controls. Enables us to do manual remediation | Low | Cloud Admin
R5 | Unencrypted Data at Rest Sensitive financial data stored without encryption | A.10 | 2 – Medium | 3 – High | 6 | MEDIUM | SSE-KMS enforced via bucket policy; AWS Config rule validates encryption compliance | Low | Security Team
R6 | Unauthorized API Activity Malicious or accidental API calls compromising resources | A.12, A.16 | 3 – High | 3 – High | 9 | HIGH | CloudTrail logs all API activity globally. CloudWatch metric filters detect unauthorized calls. SNS alerts dispatched in real-time. Lambda triggers automated response or enrichment; security team performs investigation | Low | Security Team
R7 | CloudTrail Logging Disabled Audit trail tampered with or disabled by insider threat | A.12 | 1 – Low | 3 – High | 3 | LOW | CloudWatch alarm detects StopLogging events and triggers immediate SNS alert; log file integrity validation enabled | Low | Cloud Admin
R8 | MFA Bypassed or Disabled Authentication weakened through MFA removal | A.9 | 1 – Low | 3 – High | 3 | LOW | CloudWatch alarm: DeactivateMFADevice triggers SNS alert immediately. AWS Config rule iam-user-mfa-enabled evaluates continuously. IAM policy requires MFA for sensitive actions. | Low | Security Team
R9 | Data Loss or Accidental Deletion Accidental deletion of critical data or audit logs | A.12.3 | 2 – Medium | 2 – Medium | 4 | MEDIUM | S3 versioning enabled on all data and log buckets. CloudTrail 365-day retention policy. Delete protection via bucket policy restricting delete permissions. | Low | Cloud Admin
R10 | KMS Key Compromise Encryption keys leaked, stolen, or improperly managed | A.10 | 1 – Low | 3 – High | 3 | LOW | AWS KMS customer-managed keys. Key access restricted by KMS policy. Automatic annual rotation enabled. CloudTrail logs all key usage events. | Low | Security Team
Risk Scoring Legend |  |  | Score → Risk Level
1 – Low | Unlikely / Minor impact |  | 1-3 | LOW
2 – Medium | Possible / Moderate impact |  | 4-6 | MEDIUM
3 – High | Likely / Severe impact |  | 7-9 | HIGH